SCREENWEST KEY PERFORMANCE INDICATORS

The Key Performance Indicators are taken from the ScreenWest Operational Plan, which is based on the ScreenWest Strategic Plan 2006-2011.

1.1	Strategic Communications

ScreenWest will foster recognition of the screen industry as a critical cultural, and growing economic, contributor to the WA community, while associating our ScreenWest brand with leaders and leading initiatives in the industry.

| Activity | KEY PERFORMANCE INDICATORS | Actual in 06-07 | Goal 07-08 | Actual as at 31/12/07 | Measurement Frequency |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 Manage media coverage of ScreenWest initiatives and WA productions/ companies | KPI: Increased number of favourable media articles. 4 Year Target: 10% increase per annum | *172 *As from Sept 06 | 200 | 202 | Quarterly |
|  | KPI: Decreased number of negative media articles. 4 Year Target: 10% decrease per annum | 7 *As from Sept 06 | 6.3 | 16 | Quarterly |

Commentary

The first quarter had a large number of positive articles on Baz Luhrmann’s production of Australia in the Kimberley region.  A number of these articles mentioned the three ScreenWest Professional Attachments on the production as well as the spill-on benefits to the local community.  The second quarter press covered the Western Australian AFI nominations, in particular the AFI Award win for David Ngoombujarra for his supporting role on The Circuit.  Additional 2nd quarter positive articles related to the increased number of feature films being shot in Western Australia and drama series such as The Circuit, Marx & Venus and The Sleepover Club.   The increase in the number of negative articles in the second quarter was largely attributable to ScreenWest’s withdrawal of funding from the feature film Two Fists One Heart and some critical clippings relating to Home Song Stories not being funded or shot in Western Australia.

| Activity | KEY PERFORMANCE INDICATORS | Actual in 06/07 | Goal 07/08 | Actual as at 31/03/08 | Measurement Frequency |
| --- | --- | --- | --- | --- | --- |
| 1.2.1 Facilitate increased availability of annual funds for the industry. | KPI: Increased number of new partnership opportunities explored/facilitated by ScreenWest. 4 Year Target: At least four new avenues of additional funding facilitated. Aspirational Goal: 50% increase in screen industry revenue secured by 2011 | New measure in 07/08 | 10 | 8 | CEO provides written report (See CEO’s commentary below) |
| 1.2.2 Increase availability of annual funds for ScreenWest | KPI: Increased annual funds for ScreenWest. Aspirational Goal: 50% increase in ScreenWest revenue secured by 2011 (to achieve Strategic Plan aims) | New measure in 07/08 |  | CPI + $500,000 over 4 years on Lotterywest funding $3.2Million secured under the Ignite Package | CEO provides written report |

CEO’s Commentary

1.2.1	 In the nine months to December 2007, funding submissions were commenced/progressed with:

PIAF

ScreenWest commenced discussions as to how the two bodies may be able to work together in future years, and in particular as to whether PIAF can have a focus that may include films.  Negotiations will continue in the New Year.

PIAF also agreed to screen a number of short Western Australian films as part of the Lotterywest Film Season.

Digital Content Study (Department of Culture and the Arts (DCA))

Funding of $10,000 was received to assist the production of a scoping study for the development of the case for greater investment in digital content.

DCA has also commenced undertaking a review (at no cost) of ScreenWest’s Funding Team’s practices.

Zhejiang Cultural Exchange

Funding of $130,000 was committed to the production of the Zhejiang cultural exchange documentary sourced from the Department of Industry and Resources (DoIR) with assistance from the DCA.

Funding of $3,000 was also received from DoIR to assist the cost of the production of a survey of the size of the animation industry in Western Australia.

RGM

RGM Entertainment (Singapore) is an executive production, media and film financing and talent management company for the global film market.  It is proposing to bring its unique combination of expertise and knowledge into WA and is seeking to raise 10% of its proposed USD$100m rolling fund from the Western Australian (WA) government.

ScreenWest has been working with DoIR to put the opportunity before Government.

Further work will be undertaken on this initiative in the final quarter.

SBS – the Destination Australia initiative

Destination Australia is a ScreenWest production development initiative jointly funded with SBSi and other interstate funding bodies.  It is intended to provide opportunities for an early/mid career Western Australian producer and director to make a one hour documentary for national TV broadcast.

Nickelodeon

Negotiations commenced for the creation of an animation production initiative with Nickelodeon.  An in-principle agreement is close to finalisation with ScreenWest, Nickelodeon and the Film and Television Institute.  It is hoped contracting can be completed by the middle of the year and initiative “kick-off” in the third quarter of 2008.

VIA

ScreenWest secured funding of $100,000 from the Department of Culture and the Arts for a new initiative with the ABC entitled Via.  The project aims to create digital arts production collaborations between Western Australian arts companies / practitioners / industries and digital content producers.  The content produced will be published on ABCTV multi-platforms.

ACDI

The ACDI is an information communication technology (ICT) and digital content production joint venture initiative between Western Australian companies, ISA Technologies (based at Technology Park) and the Vue Group. This involves high powered super computing with leading edge digital media technicians to produce world leading special effects for film, television and other media.

ScreenWest has facilitated a relationship with the consortia and DoIR.

DoIR has provided $25,000 towards part of the costs of a Scoping Study.  After completing the Scoping Study, ACDI now needs to prove the viability of its concept, and to commence work on a test in the fourth quarter of this financial year.  ScreenWest will continue to work with the consortia to secure funding for the concept.

The Scoping Study outlined that the ACDI will be a major asset and attraction factor for the local ICT/ digital content industry. The ACDI will bring about:

    - an increase in digital content productivity and quality;

    - skilled employment;

    - value-adding activities;

    - trade and export;

    - global recognition;

    - greater involvement in international animation projects/ players;

    - development and retention of intellectual property for Western Australia; and

    - significant multipliers to the economy.

1.2.2	As Lotterywest is aware, new funds of $500,000 over the next four financial years were secured from Lotterywest, together with a CPI increase on the base funding provided to ScreenWest.

ScreenWest received $3.2M under the Premier’s Ignite package, to be cashflowed over the 08/09 and 09/10 financial years.

ScreenWest has also made a budget bid to Government for new funding for investment into digital content.

| Activity | KEY PERFORMANCE INDICATORS | Actual in 06/07 | Goal 07/08 | Actual as at 31/03/2008 | Measurement Frequency |
| --- | --- | --- | --- | --- | --- |
| 1.3.1 Increasing total value of production on ScreenWest funded projects | KPI: Increased total production budget value of projects funded by ScreenWest. 4 Year Target: A sustainable level of $40M per annum | $21.86M | $40M | $19.16M (Conservative final estimated position for the year as at 31/12/07 $40M) | Quarterly (13 Projects entered principal photography between 01/07/2007 and 31/03/2008: The Feature Films - To Hell & Bourke and Two Fists One Heart which received development funding only. Single Documentaries – The Fabulous Flagg Sisters, Kitchen to the Courthouse, God Made them Blind Gallipoli’s Submarine, A Million Puppets, The Modernity Paradox and The Hunt for HMAS Sydney and Documentary Series, Desperately Seeking Doctor, Snakebusters 2, Navy Divers and Generation Y Series. |
| 1.3.2 Increasing total value of production expenditure in Western Australia on ScreenWest funded projects | KPI: Increased total value of production expenditure in WA. 4 Year Target: A sustainable level of $30M per annum. | $16.3M | $25M | $10.8M (Conservative Estimated final position for the year $24mil) | Quarterly Figures based on the projects listed under 1.3.1 |

| Activity | KEY PERFORMANCE INDICATORS | Actual in 06/07 | Goal 07/08 | Actual as at 31/03/2008 | Measurement Frequency |
| --- | --- | --- | --- | --- | --- |
| 1.3.3 Develop projects with greater likelihood of being produced | KPI: Increased percentage of ScreenWest funded projects go into production. 4 Year Target: 35% by 2011. | 24.1% | 26% | 26% (See table and graph below) | Quarterly |

| PROJECTS | 2003/2004 | 2004/2005 | 2005/2006 | 2006/2007 | 2007/2008 (As at 31/03/2008) |
| --- | --- | --- | --- | --- | --- |
| Total No. of projects (All genres developed by ScreenWest) | 201 | 213 | 254 | 282 | 298 |
| No. Projects (Produced) | 40 | 47 | 58 | 68 | 77 |
| Total % (Success rate) | 19.9% | 22.06% | 22.83% | 24.11% | 26% |

| Activity | KEY PERFORMANCE INDICATORS | Actual in 06/07 | Goal 07/08 |  |  | Actual as at 31/03/2008 | Measurement Frequency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3.4 Maximising expenditure in Western Australia | KPI: Increase in ScreenWest average investment ratio of ScreenWest expenditure to the total expenditure in WA. 4 Year Target: 1:5 to be achieved by 2011. | 1:4.5 | 1:4.5 |  |  | 1:5.6 | Quarterly Based on projects that have entered principal photography between 01/07/2007 and 31/03/2008.. ScreenWest’s investment of $1,912,198 has geared up WA expenditure of $10,800,375 |
| 1.3.5 Maximising employment of Western Australian residents | KPI: Increased number of WA Key Creatives employed on ScreenWest productions. Aspirational Goal: 75% by 2011. | 50.6% | 55% |  |  | 70% (40 out of 57 key creatives are WA) | Quarterly Figures are unusually high during the first half due to two projects (Generation Y & Kitchen to the Courthouse) being funded under early career special initiatives that require all Key Creatives to be WA residents. However, ScreenWest Management has been working hard with PC’s to ensure the maximum no. of local key creatives are employed. |
| 1.3.6 Assist career pathways for Western Australian Indigenous filmmakers | KPI: Increased number of WA Indigenous filmmakers securing production funding from a Federal body (i.e. FFC or AFC). 4 Year Target: 10 funded per annum | 3 |  | 4 | 2 |  | Quarterly (Debbie Gittens Director & Lynette Narkle Writer) Kitchen to the Courthouse. No increase this quarter |
| 1.3.7 Assist career pathways in key creative positions for Western Australian Indigenous Filmmakers | KPI: Increased number of WA Indigenous key creative filmmakers employed as a Key Creative on short films funded by ScreenWest. 4 Year Target: 10 employed per annum | 15 |  | 10 | 0 |  | Quarterly (Deadly Yarns will occur later in the current financial year – also ScreenWest is likely to co-fund short film production with the AFC) |
|  | KPI: Increased number of WA Indigenous key creative filmmakers employed on productions other than short films. 4 Year Target: 10 employed per annum | 4 |  | 5 | 4 |  | Quarterly To Hell & Bourke (Taryn Laffar – Extra Casting Coordinator, Gary Cooper – Directors Assistant & Cultural Liaison, Brett Cullen – Split Screen Operator Australia – Arnhem Hunter - Grip |
| 1.3.8 Develop cross platform/digital production | KPI: Increase in projects, with an alternative delivery platform, of 1 hour duration or more, entering into principal photography during 07/08. 4 Year Target: 40% by 2011. | 5/14 (35%) |  | 35% | 1/10 (10%) |  | Quarterly Generation Y has a cross platform delivery component (Both game and website) |

1.4	Industry Development

ScreenWest will lead the facilitation of knowledge-sharing and craft development of talented screen practitioners in the WA screen-media industry, by working with other professional bodies to ensure WA industry members excel in their timely application of new technologies and sustain a high level of global competitiveness.

| Activity | KEY PERFORMANCE INDICATORS | Actual in 06-07 | Goal 07-08 | Actual as at 31/12/07 | Measurement Frequency |
| --- | --- | --- | --- | --- | --- |
| 1.4.1 Facilitating key conferences and events in Western Australia | KPI: Increased number of attendees at WA conferences and events. 4 Year Target 10% increase per annum | *22,904 *Inclusive of training, (which will be broken down in future) | *25,000 *Inclusive of training, (which will be broken down in future) |  | Annually (this will be reported at the end of the financial year) |
| 1.4.2 Funding/facilitating skills training and workshops in Western Australia | KPI: Increased number of WA skills training and workshops in diverse range of key creative areas. | New measure | Next years goal set on this years outcomes |  | Annually (this will be reported at the end of the financial year) |
| 1.4.3 Achieving Awards for ScreenWest funded projects | KPI: Increased number of nominations in key Australian Awards (i.e. AFI, Logies, IF Awards and AWGIES). 4 Year Target: Sustained level of 5 people per annum | 1 | 3 | 17 | Quarterly AWGIE nominations during 1st quarter (Renee Webster for her Filmex short film Edgar & Elizabeth and The Circuit for original Screenplay for a Television Mini-Series. AFI nominations during 2nd quarter. 11 Nominations and two awards received. One for Lockie Leonard best Children’s Drama Series and David Ngoombjarra won for best supporting actor for The Circuit. 3rd quarter –4 Logie nominations. Tammy Clarkson public-voted Most Popular New Female Talent award, as well as the Graham Kennedy Award for Most Outstanding New Talent for The Circuit. Sean Keenan has been nominated for the Graham Kennedy Award for Most Outstanding Talent for Lockie Leonard and Lockie Leonard has been nominated for the Most Outstanding Children's Program |

- 1.5.	ScreenWest is a Dynamic Organisation

The ScreenWest team will exhibit an entrepreneurial, progressive and innovative spirit as it helps build solutions for the screen industry.  ScreenWest will be open, transparent and accountable and listen to its stakeholders, adjusting its structure, staff skill sets and evolve its policies/processes, to assist the fast-changing screen industry and to advance the industry in WA.

| Activity | KEY PERFORMANCE INDICATORS | Actual in 06-07 | Goal 07-08 | Actual as at 31/12/07 | Measurement Frequency |
| --- | --- | --- | --- | --- | --- |
| 1.5.1 Conduct an assessment of client satisfaction with ScreenWest’s services | KPI: Qualitative improvement in online survey results on ScreenWest’s ability to meet client needs. 4 Year Target: Qualitative improvement per annum Aspirational Goal: ScreenWest regarded as a benchmark leader in client responsiveness. | New measure | Next years goal set on this years outcomes |  | Annually |
| 1.5.2 ScreenWest is responsive to client needs | KPI: Decreased number of formal appeals. 4 Year Target: 25% decrease per annum Aspirational Goal: No formal appeals | 4 | 3 | 0 | Annually No formal appeals as at 31/03/08 |