Operational Plan

CRITICAL SUCCESS FACTOR 1		STRATEGIC COMMUNICATIONS

ScreenWest will foster the recognition of the screen industry as an important cultural and growing economic contributor to the WA community; connecting with leaders of other major economic sectors, private investors and Government Departments.

  - increased recognition and profile of the local industry and ScreenWest and its services

  - strengthen and develop strategic collaborations

| Activity | Who | Timeframe | Progress/Status | KPI | Measurement of KPI | Progress/Status | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 Achieve media coverage for ScreenWest initiatives and support local production companies to secure local and national media coverage | Communications Team | Ongoing | Ongoing | No. of press articles/broadcast coverage achieved in a 12 month period. *note this figure will be dependent on production activity. | Use Media monitoring reports. (Report every three months to key stakeholders). |  | Resourced through Communications staff |
| 1.1/1.2 Host /support production companies with screening launches and other events with key stakeholders and invited media | Communications Team | Ongoing | Analyse initiation list for each event - ongoing | Successful events with Increased attendance by key stakeholders/ potential partners. | Six monthly report of events, including attendance and qualitative feedback from selected stakeholders. |  | Current budget allocation sponsorship and events |
| 1.2 Investigate potential partnerships and cross-collaboration between the screen industry and other arts and culture / industry areas. | CEO/Communications Team | Initial exploration results by the end of 2007 | Not started | Submit report on potential cross-collaborations and intended benefits | Report drafted and provided to CEO /SW Board |  | No budget allocation – greater resources required |
| 1.3 Provide the ScreenWest Board, Lotterywest, DCA, and the Minister’s office with quarterly reports on communications and other key strategic activities. | Communications Team / Executive Team | Start beginning financial year 07/08 | Not started | Activity statement presented to key stakeholders quarterly. Member of Executive Team to meet with a representative from each key stakeholder by the end of FY 07/08 | Reports signed off on by key stakeholders. Member of Executive Team |  | Resourced through Communications staff |
| 1.3 Ensure the Ensure the new ScreenWest website and new look Screen Online provide enhanced services to industry and have more user friendly interface. | Communications Team *information campaign re new look website and Screen Online to commence Sept 07 | Draft content and web site map finalised by the start of 07/08 financial year | Content in final draft form – draft site map done | New website and Screen Online up and running by September 07 with enhanced services for industry | Survey to industry members/stakeholders - results stating improved interactivity of web site / Screen Online (end calendar year 07) |  | Resourced in Communications budget |

CRITICAL SUCCESS FACTOR 2			FINANCIAL

ScreenWest will work with Government and externally with private investors, including the corporate sector, to enhance and secure the ongoing availability of annual investment funds available to the WA screen industry.

ScreenWest will lead and facilitate the exploration of international partnerships and market development.

  - Increased Funding - Australia

  - Initiate International Partnerships

| Activity | Who | Timeframe | Progress/Status | KPI | Measurement of KPI | Progress/Status | 2007/08 Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 Increased Funding – Australia |  |  |  |  |  |  |  |
| General Development and Production Funding WA on Screen | CEO |  | Funding committed in the budget at $2M per annum until 2010/11. Need to evaluate whether we need to increase funding, suggest 2009. | Funding secured | Funding secured yes/no | N/A On hold | From within Administrative services |
| Indigenous | CEO | On-going | Main funding source is Lotterywest funds – additional $200,000 to be secured by September 2007. Various other potential sources for the future. | New Funds Secured | Funding secured yes/no |  | From within Administrative services |
| Lotterywest | CEO | June 2007 – September 2007 | Application with Lotterywest; seeking response by July Board | New Funds Secured | Funding secured yes/no |  | From within Administrative services |
| Market Partnership Funding - ABC Fund | CEO | September 2007 | Seeking to clarify timeframe with the Minister. Also seeking to commit to the remainder of the current funds. | New Funds Secured | Funding secured yes/no | N/A | From within Administrative services/potentially some limited travel funds |
| Production Attraction | CEO | On-going | Currently two projects in train, assessing future opportunities | New Funds Secured | Funding secured yes/no |  | From within Administrative services/potentially some limited travel funds |
| Digital Development and Production/Innovation Fund | CEO | July - September 2007 Then End 2008 | Initial plan is to secure the new funds from Lotterywest, develop a budget bid for a Digital Content Fund from the State Government | Submission to Lotterywest and Government New Funds Secured | Funding secured or not |  | From new funding submission to Lotterywest - $100,000. |
| DOIR | CEO with assistance from DPD | On-going | Close working relationship established, continuing to identify opportunities and work with DOIR | Relationship ongoing for mutual benefit. | Funding secured or not |  | From within Administrative services |
| DCA Resources | CEO and COO | On-Going | Seeking to improve relationship and resources received from DCA | Relationship ongoing for mutual benefit. Increase in resources received. | Funding secured or not |  | From within Administrative services |
| 2.1.3 Corporate Partnerships - PIAF - Potential corporate sponsorships | CEO CEO/ Comms Team | September 2007 Commence Jan 2008 | Develop strategic relationship with PIAF Develop targets and strategy | Agreement reached on initial project |  |  | Potential budget implications - $15,000 included in draft budget. |
| 2.2 Initiate International Partnerships | CEO | Commence January 2008 | Develop targets and strategy | International partnerships secured | ??? |  | From within Administrative services/potentially some limited travel funds |

CRITICAL SUCCESS FACTOR 3		TARGETED FUNDING PROGRAM

ScreenWest will work with the industry to advance innovation and creativity in key production genres, particularly the amount of cross platform, including interactive and on-line production, taking into account the advantages and strengths of the WA screen industry, with the goal of securing increasingly sustainable production slates.

  - Target funding programs to support the development of people, projects and businesses in key production genres

  - Create and develop strategic Indigenous production initiatives

  - Proactively develop emerging production genres.

Target funding programs to support project development and Production Fund and Production Development Initiatives as well as Production Company Support.

NB:  the bolded numbers below relate to the three enumerated tasks listed above to achieve Critical Success Factor 3.

| Activity | Who | Timeframe | Progress/Status | KPI | Measurement of KPI | Progress/Status | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 Project Development 1. Successfully Administer schemes & budget. 2. Annually review each initiative including outcomes and revise guidelines accordingly | Liz Sward, Victor Gentile, Producer Intern and Harry Bardwell | All schemes to be reviewed by end of financial year – and revised guidelines to be ready for commencement of new financial year. | Set calendar for review by end of 07/08 financial year – Funding Team | A % increase in the number of projects that have received development funding from ScreenWest going into production. Review of initiative and guidelines by end of 2007. (NB: this KPI applies to all funding initiatives). | Annual measurement at the end of financial year Guidelines reviewed by end of 2007. Implementation in first half of 2008. (NB: applies to all initiatives). |  | $506,000 |
| 3.1 Production Fund 1. Successfully Administer schemes & budget. 2. Annually review each initiative including outcomes and revise guidelines accordingly | Liz Sward, Victor Gentile, Producer Intern and Harry Bardwell | All schemes to be reviewed by end of financial year – and revised guidelines to be ready for commencement of new financial year. | Set calendar for review by end of 07/08 financial year – Funding Team | ScreenWest’s investment ratio to WA expenditure exceeds 1:4. (NB: need to determine the average before finalising this KPI). | Annual measurement at the end of financial year. |  | $3,100,000 |
| 3.1 Production Development Initiatives 1. Successfully Administer schemes & budget. 2. Annually review each initiative including outcomes and revise guidelines accordingly | Liz Sward, Victor Gentile, Producer Intern and Harry Bardwell | All schemes to be reviewed by end of financial year – and revised guidelines to be ready for commencement of new financial year. | Set calendar for review by end of 07/08 financial year – Funding Team | Increase to 75% the number of WA key creatives working on ScreenWest Production Fund supported projects. (NB: need to determine the average before assessing the extent of this KPI). | Annual measurement at the end of financial year | Not measured previously – 06/07 measurement required to set benchmark. | $1,630,000 |
| 3.1 Production Company Support – 1. Successfully Administer schemes & budget. 2. Annually review each initiative including outcomes and revise guidelines accordingly Annually review each initiative including outcomes and revise guidelines accordingly | Liz Sward, Victor Gentile, Producer Intern, Harry Bardwell & Ian Booth | All schemes to be reviewed by end of financial year – and revised guidelines to be ready for commencement of new financial year. | Set calendar for review by end of 07/08 financial year – Funding Team | At least one new company supported under Business Development schemes per financial year. NB: PEP Scheme must be reviewed prior to the above measure being implemented. | Annual measurement at the end of financial year. |  | $540,000 |
| 3.1 Practitioner Development 1. Successfully Administer schemes & budget. 2. Annually review each initiative including outcomes and revise guidelines accordingly Annually review each initiative including outcomes and revise guidelines accordingly | Liz Sward, Victor Gentile, Producer Intern, Harry Bardwell & Ian Booth | All schemes to be reviewed by end of financial year – and revised guidelines to be ready for commencement of new financial year. | Set calendar for review by end of 07/08 financial year – Funding Team | Uptake of producer Internship into industry employment is at 100%. A % increase in local ongoing employment. (NB: need to benchmark the number of employed persons before utilising this KPI). | Annual measurement at the end of financial year. |  | $339,452 |
| 3.2 Create and develop strategic Indigenous production initiatives 1. Successfully Administer schemes & budget. 2. Annually review each initiative including outcomes and revise guidelines accordingly Annually review each initiative including outcomes and revise guidelines accordingly | Debra Miller and Harry Bardwell | All schemes to be reviewed by end of financial year – and revised guidelines to be ready for commencement of new financial year. | Set calendar for review by end of 06/07 financial year – Debra Miller. | A % increase in the number of successful local Indigenous filmmakers who receive Federal Funding. (NB: need to benchmark the number of employed persons before utilising this KPI). | Annual measurement at the end of financial year. |  | $540,000 |
| 3.2 – Create and administer/or partner in an Indigenous long form production Initiatives for Broadcast. | Debra Miller and Harry Bardwell | By December 2007 | Set Calendar for review by end of 07/08 | An increase in the number of Indigenous key creatives involved in the production of a long form project for broadcast. | Annual measurement. 06/07 measure forms basis for comparison. |  | Within $540,000 Indigenous allocation above unless additional funds are sourced. |
| - Cross Platform Production - Proactively develop emerging production genres - Proactively develop emerging production genres. | Harry Bardwell | By December 2007 |  | An % increase in the number of SW funded productions that include an alternative delivery platform (eg. website, game). | Annual measurement. 06/07 measure forms basis for comparison. |  | $100,000 |

CRITICAL SUCCESS FACTOR 4		INDUSTRY PROFESSIONAL DEVELOPMENT AND TRAINING

ScreenWest will work with other professional bodies to facilitate the knowledge-sharing and craft development of talented screen practitioners in the WA screen-media industry, to ensure that WA industry members remain relevant, timely in their application of new technologies and globally competitive.

  - Undertake a training needs analysis for the WA screen industry

  - Initiate and support key cultural activities, Conferences &  Events (Screen Culture)

  - Support targeted industry development and training

| Activity | Who | Timeframe | Progress/Status | KPI | Measurement of KPI | Progress/Status | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 Training |  |  |  |  |  |  |  |
| Coordinate industry professional bodies & other stakeholder organisations to examine training requirements in a dynamic environment ; examine existing training offered, undertake gap analysis and make recommendations to stakeholders | Ron Couacaud to coordinate in consultation with stakeholders like FTI etc. (NB: ScreenWest may support external consultant or some other body to undertake – to be considered). | 12-18 months |  | TNA undertaken and recommendations provided to the Board and other stakeholders | TNA undertaken yes/no |  | No budget allocation at this moment – needs further discussion by Management Team |
| 4.2 Screen Culture | Communications Team | Commenced initial report of events sponsored under Screen Culture fund over past three years | Review and evaluate sponsored events, conferences, workshops, and film festivals under the Screen Culture banner, including SSBP. | An increase in attendance at Screen Culture events by Western Australians over a 12 mth period. *Need to benchmark numbers attending. *Build in a feedback mechanism in contracts to measure event effectiveness | Number of West Australians attending increase in numbers yes/no Review of appreciation and effectiveness of conferences, events etc. |  | $167,000 |
| AIDC | Management Team | July 07 - Feb 2008 | Event managed by AIDC, negotiating current funding agreement | Attendance and Quality of event | As per above, plus total attendance. |  | $80,000 (from 07/08 budget) |
| 4.3 Resource Organisations (Core funding only) | Management Team | On-going | Evaluate and administer support to resource organisations. | Funding and outputs of Resource Organisations evaluated. Number of training attendees. |  |  | [$665,395 – just FTI] |

CRITICAL SUCCESS FACTOR 5		SCREENWEST IS A DYNAMIC ORGANISATION

The ScreenWest team will exhibit an entrepreneurial, progressive and innovative spirit as it helps build solutions for the screen industry businesses it invests in and supports. ScreenWest will adjust its structure, staff skill sets and evolve its policies/processes to assist the fast-changing screen industry and to advance the industry in WA.

  - Structure systems and organizational policies to reflect the priorities of the living strategic plan

  - ScreenWest staff will be encouraged to develop and perform to their potential

  - Ensure ScreenWest is responsive to client needs

| Activity | Who | Timeframe | Progress/Status | KPI | Measurement of KPI | Progress/Status | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Review Strategic Plan annually. Use environmental scanning and SWOT analysis along with other techniques. As a result of above, consider if structure still congruous with strategy, policies plans and demands of customers. | Management Team | (i) When formulating budget submissions to Minister approx September (ii) Part of mid year budget review process In early to mid January) |  | Review undertaken. | Review undertaken – yes/no | Ongoing. To be undertaken in January 2008 and January each year from then on. | Budget will reflect Strategic and Operational Plan |
| Provide staff with encouragement, guidance and performance feedback regularly on an informal basis and formally through the Staff Development System | Management Team | Ongoing |  | Staff Reviews (SDS) undertaken with 2 way feedback on achievements, problem / issue identification and personal and professional growth | SDS process undertaken (Objective) Staff indicate informally that their job is satisfying and challenging, that they are helped when required and feel valued. (Subjective) | Ongoing as part of formal SDS process and informally as normal part of supervision and interaction among team members. | Training budget ($20,000) has been increased as a result of introduction of SDS. HDA requirements partly built into budget. Relief staff allocation in budget. |
| Conduct regular (annual) customer satisfaction surveys | Ron Couacaud, with assistance from Liz Sward and Louise Merrilees | Annual, or more regular if funds / needs allow |  | Survey undertaken | Survey undertaken yes/no |  | Survey currently undertaken trough Arts Monitor. A different survey would require new funding. No funds available at this time. |
| Organisational KPIs and other workload Statistics | Ron Couacaud with assistance from Liz Sward, in particular. Overall review by Management Team | Annual Reporting to Government. More frequent to Board and Lotterywest |  | KPIs reviewed and established and relevant information collected. | KPIs established and measurement activities undertaken |  | No specific budget allocation at this stage. |

Appendix One – Brief details of Funding Program Initiatives

Funding Program is divided into –

Project Development

Matched Development Investment Funding
General Development Investment Funding
Project Development Investment Funding (Features)

Emergency Funding
State Location & Crew Support Services

Production Funding

Production Funding
Film & TV Production Fund – ABC Fund

Production Development Initiatives

West Coast Visions

TV Co-Productions
Link & Hyperlink

Making Movies Roadshow

Short film or Self Funded Low Budget Feature Marketing

Production Company Support

Producer Enterprise Package

Travel & Marketing

Practitioner Executive Development

Practitioner Development Travel

Practitioner Development Travel Grants

Professional Attachments and Mentorships

Producer Internship
AFTRS/Courses

Writers Development Initiatives

Bill Warnock New Feature Writers Award

Television Writes Awards

Digital Directions Award

Indigenous production - Create and develop strategic Indigenous production initiatives

Indigenous Initiatives

- Deadly Yarns (with FTI)

- Index

- NIDF

- Community Stories

- National Drama

Cross Platform - Proactively develop emerging production genres.

- Digital Initiative